## SDD Work Log
Day | Date | SDD Lifecycle Stage | Planned Deliverable | Actual Output / Artifact Link | Hours Spent | Notes / Blockers
Day 1 | 2026-08-29 | Discovery & Requirement Analysis | Requirement extraction, business vs technical decisions, project context setup | .ai-context/BRD.md, .ai-context/constitution.md, .ai-context/status.md | 3 | Initialized WordPress stack constraints, authored BRD-001, and defined business and technical boundaries.
Day 2 | 2026-08-30 | Specification Authoring | Feature specification skeleton & Gherkin ACs | .ai-context/specs/emp-internal-transfer.spec.md | 3.5 | Defined 8 testable acceptance criteria (AC01–AC08) covering eligibility, sequential approvals, and access isolation.
Day 3 | 2026-08-31 | API Contracts & Spec-Derived Test Cases | API payload schemas, exception tables, and test cases | .ai-context/specs/emp-internal-transfer.spec.md, .ai-context/test_cases/emp-internal-transfer.test_cases.md | 3.5 | Completed REST contracts (API01–API03) and mapped test scenarios (UT01–UT08) for Gate 1 readiness.
Total Hours